## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE
PROJECT TITLE |  |  | Shabu for u | [9 empty] | COMPANY NAME |  | Shabu for u
PROJECT MANAGER |  |  | Mr.Wattana Pongpaew | [9 empty] | START DATE |  | 1 September 2020
PROJECT DURATION | [12 empty] | END DATE |  | 15 December 2020
[16 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
WBS NUMBER | TASK TITLE |  | TASK OWNER | [8 empty] | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[16 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation Phase | Customer | PM | BA | SA | DEV | SE | UX | QA | Trainer | IT Support
1.1 | Project Organization | [10 empty] | 15/08/2020 | 17/08/2020 | 3 | 100%
1.1.1 | Project Charter Revisions |  | P | [8 empty] | 17/08/2020 | 17/08/2020 | 1 | 100%
1.1.2 | Progress meeting # 2 |  | P | P | P | P | P | P |  |  | P | 17/08/2020 | 17/08/2020 | 1 | 100%
1.2 | HW, SW and Network preparation |  | P | [8 empty] | 17/08/2020 | 23/08/2020 | 7 | 100%
1.2.1 | Hardware and Network preparation | [5 empty] | P |  |  |  | P | 17/08/2020 | 23/08/2020 | 7 | 100%
1.2.2 | Software preparation |  |  |  |  | P | P |  |  |  | P | 17/08/2020 | 23/08/2020 | 7 | 100%
1.3 | Review Scope of work
1.3.1 | Scope of Work Revisions - Product Data |  | P | P | P | [6 empty] | 17/08/2020 | 23/08/2020 | 7 | 100%
1.3.2 | Scope of Work Revisions - Operation for Admin |  | P | P | P | [6 empty] | 17/08/2020 | 21/08/2020 | 5 | 100%
1.3.3 | Scope of Work Revisions - Operation for Customer |  | P | P | P | [6 empty] | 17/08/2020 | 21/08/2020 | 5 | 100%
2 | Requirement Gathering
2.1 | Get Requirement & Discussion |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.1 | ในฐานะแอดมิน
2.1.1.1 | สามารถล็อคอินเข้าสู่ระบบได้ |  |  | P | [7 empty] | 18/08/2019 | 31/08/2019 | 14 | 100%
2.1.1.2 | สามารถสนทนากับลูกค้าผ่านช่องทางแอปพลิเคชั่นได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.1.3 | สามารถสร้างรหัสส่วนลดให้ลูกค้า |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.1.4 | สามารถเพิ่มข้อมูลเซ็ตชาบูลงในเมนูได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.1.5 | สามารถแก้ไขเซ็ตชาบูในเมนูได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.1.6 | สามารถลบเซ็ตชาบูออกจากเมนูได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.1.7 | สามารถแก้ไขรหัสส่วนลดได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.1.8 | สามารถลบรหัสส่วนลดได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.1.9 | สามารถล็อคเอาท์จากระบบได้ |  |  | P | [7 empty] | 18/08/2021 | 31/08/2021 | 14 | 100%
2.1.2 | ในฐานะลูกค้า
2.1.2.1 | สามารถล็อคอินเข้าสู่ระบบได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.2 | สามารถแก้ไขข้อมูลส่วนตัวได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.3 | สามารถเลือกเซ็ตชาบูได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.4 | สามารถแก้ไขออเดอร์ในตะกร้าสินค้าได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.5 | สามารถยกเลิกออเดอร์ได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.6 | สามารถเลือกเวลาในการจัดส่งได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.7 | สามารถเลือกตำแหน่งในการจัดส่งได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.8 | สามารถกรอกรหัสส่วนลดได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.9 | สามารถให้คะแนนร้านชาบูได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.10 | สามารถสนทนากับแอดมินผ่านช่องทางแอปพลิเคชั่นได้ |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.2.11 | สามารถล็อคเอาท์จากระบบได้ |  |  | P | [7 empty] | 18/08/2021 | 31/08/2021 | 14 | 100%
2.1.2 | Requirement Development |  |  | P | P | [6 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.3 | Summarize Requirement & Meeting | P | P | P | [7 empty] | 2020-09-03 | 2020-09-03 | 1 | 100%
2.2 | Summarize Source of Data
2.2.1 | Define Data Source for Product Data | P | P | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.2.2 | Define Data Source for Operation | P | P | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.2.3 | Data Source Sign-off Meeting | P | P | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
3 | Analysis and Design Phase
3.1 | System flow Design |  |  |  | P | [6 empty] | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2 | User Interface Design | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.1 | Sing in page | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.1.1 | Input e-mail | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.1.2 | Input password | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.2 | Sign up page | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.2.1 | Input e-mail | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.2.2 | Input password | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.2.3 | Input full name | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3 | Home page (index) | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1 | Navigation bar (All page) | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.1 | " Home " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.1.1 | Package Shabu set | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.2 | " Delivery " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.2.1 | Delivery detail | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.2.2 | " Cancel " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.2.3 | Review Order | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.2.4 | " Preview " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3 | " Order " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.1 | " Add " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.2 | " Remove " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.3 | Shabu set detail | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.4 | " Checkout " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.5 | " Edit address " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.6 | " Edit time " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.7 | " Edit order " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.8 | " Pay by cash " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.9 | " Pay by credit card " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.3.10 | " Input promotion code " Input text | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.4 | " Chat " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.4.1 | " Chat " Input text | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.4.2 | " Send message " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.5 | " Profile " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.5.1 | " History " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.5.2 | " Edit profile " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.5.3 | " Address " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.5.4 | " Promotion " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.5.5 | " Setting " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.2.3.1.5.6 | " Log out " button | [6 empty] | P |  |  |  | 2020-09-09 | 2020-09-22 | 14 | 100%
3.3 | Architectural Design |  |  |  | P | [6 empty] | 2020-09-09 | 2020-09-22 | 14 | 100%
3.4 | Detailed Design |  |  |  | P | [6 empty] | 2020-09-09 | 2020-09-22 | 14 | 100%
3.5 | Develop SRS document |  |  |  | P | [6 empty] | 2020-09-09 | 2020-09-22 | 14 | 100%
3.6 | SRS Sign-off Meeting | P | P | P | P | [6 empty] | 2020-09-24 | 2020-09-24 | 1 | 100%
4 | Development Phase
4.1 | Software Development |  |  | P | P | P | P |  |  |  |  | 2020-09-12 | 2020-09-25 | 14 | 100%
4.1.1 | Unit Test & Debug - Customer Operation | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.1 | ทดสอบการล็อกอิน | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.2 | ทดสอบการแก้ไขข้อมูส่วนตัว | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.3 | ทดสอบการเลือกเซ็ตชาบู | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.4 | ทดสอบการแก้ไขข้อมูลในตระกร้าสินค้า | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.5 | ทดสอบการยกเลิกออเดอร์สินค้า | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.6 | ทดสอบการเลือกเวลาจัดส่งออเดอร์สินค้า | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.7 | ทดสอบการเลือกตำแหน่งในการจัดส่ง | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.8 | ทดสอบการกรอกโค้ดส่วนลด | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.9 | ทดสอบการให้คะแนนร้าน | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.10 | ทดสอบการสนทนากับแอดมิน (Chat) | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.1.11 | ทดสอบการล็อกเอาท์ | P |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2 | Unit Test & Debug - Admin Operation |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.1 | ทดสอบการล็อกอิน |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.2 | ทดสอบการสทนากับลูกค้า |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.3 | ทดสอบการสร้างโค้ดส่วนลด |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.4 | ทดสอบการเพิ่มข้อมูลเซ็ตชาบู |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.5 | ทดสอบการแก้ไขข้อมูลเซ็ตชาบู |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.6 | ทดสอบการลบเซ็ตชาบู |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.7 | ทดสอบการแก้ไขโค้ดส่วนลด |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.8 | ทดสอบการลบโค้ดส่วนลด |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
4.1.2.9 | ทดสอบการล็อกเอาท์ |  |  |  | P | P | P |  |  |  |  | 2020-09-25 | 2020-09-29 | 5 | 30%
5 | Software Integration Test (SIT) & UAT
5.1 | Develop test scenario & test case |  |  | P |  |  |  |  | P |  |  | 27/09/2020 | 2020-10-06 | 10 | 0%
5.2 | Prepare Test Environment | [5 empty] | P |  |  |  |  | 27/09/2020 | 2020-10-06 | 10 | 0%
5.3 | System deployment on Test Environment |  |  | P |  |  | P |  |  |  |  | 27/09/2020 | 2020-10-06 | 10 | 0%
5.4 | Develop UAT documentation |  |  | P |  |  |  |  | P |  |  | 27/09/2020 | 2020-10-06 | 10 | 0%
5.5 | Training for UAT session |  | P | P | [5 empty] | P |  | 27/09/2020 | 2020-10-06 | 10 | 0%
5.6 | UAT |  | P | P | [5 empty] | P |  | 27/09/2020 | 2020-10-06 | 10 | 0%
5.7 | UAT Sign-off Meeting |  | P | P | [5 empty] | P |  | 27/09/2020 | 2020-10-06 | 10 | 0%
6 | Key User Training
6.1 | Develop administrator guide |  |  | P |  | P | [5 empty] | 2020-10-09 | 18/10/2020 | 10 | 0%
6.2 | Develop maintenance plan documentation |  | P | P | P |  | P |  |  |  |  | 2020-10-09 | 18/10/2020 | 10 | 0%
6.3 | Administrator training |  | P | P | [5 empty] | P |  | 20/10/2020 | 24/10/2020 | 5 | 0%
7 | Deployment Phase (Cut over) & Go-Live
7.1 | Prepare Production Environment |  |  | P |  |  | P |  |  |  |  | 26/10/2020 | 30/10/2020 | 5 | 0%
7.2 | Preliminaries + briefing + reserving resources (Check point, Go/NoGo) | P | P | P |  |  | P |  |  |  |  | 26/10/2020 | 30/10/2020 | 5 | 0%
7.3 | Timespan from 5 to 1 days before deployment (Check point, Go/NoGo) | P | P | P | [7 empty] | 26/10/2020 | 30/10/2020 | 5 | 0%
7.4 | Cut over (Check point, Go/NoGo) | P | P | P | [7 empty] | 26/10/2020 | 30/10/2020 | 5 | 0%
7.5 | Production test/authentication (Check point, Go/NoGo) | P | P | P | P | P | P |  |  |  |  | 2020-11-04 | 2020-11-08 | 5 | 0%
7.6 | First day in production use (Check point, Go-Live) | P | P | P | P | P | P |  |  |  |  | 2020-11-04 | 2020-11-08 | 5 | 0%
7.7 | Second day in production use (Check point, Go-Live) | P | P | P | P | P | P |  |  |  |  | 2020-11-04 | 2020-11-08 | 5 | 0%
7.8 | Support after Go-Live | [9 empty] | P | 2020-11-10 | 2021-11-09 | 365 | 0%
8 | Project Closeout (2 weeks)
8.1 | Closeout delivery |  |  | P | [7 empty] | 26/10/2020 | 30/10/2020 | 5 | 0%
8.2 | Close contract |  |  | P | [7 empty] | 26/10/2020 | 30/10/2020 | 5 | 0%
8.3 | Activate maintenance and technical support |  |  | P | [7 empty] | 26/10/2020 | 30/10/2020 | 5 | 0%
8.4 | Create project completion report |  |  | P | [7 empty] | 26/10/2020 | 30/10/2020 | 5 | 0%
8.5 | Project Closeout Meeting |  | P | P | [7 empty] | 2020-11-04 | 2020-11-08 | 5 | 0%
Note on Q7: Key % of task complete in cell and then it will generate colour bar automatically.

## Project Structure
PROJECT ORGANIZATION
PROJECT TITLE |  | Shabu For U |  | COMPANY NAME | Shabu For U
PROJECT MANAGER |  | Mr. Wattana Pongpaew |  | DATE | 2020-09-18
No | Name (EN) |  | Position in Project | Department/Division | E-mail | Phone
CUSTOMER
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
No | Name (EN) |  | Position in Project | Department/Division | E-mail | Phone
VENDOR
1 | Mr.Wattana | Pongpaew | Project Manager ,Trainer |  | s6130613027@phuket.psu.ac.th | 063-0809112
2 | Mr.Sorravit | Thongsong | Developer , System Engineer / IT Support |  | s6130613028@phuket.psu.ac.th | 095-1716431
3 | Miss Kannika | Thongnum | System Analyst , Quality Assurance |  | s6130613036@phuket.psu.ac.th | 091-0487040
4 | Mr.Nutthapon | Nisakon | UX/UI Design , Business Analyst |  | s6130613048@phuket.psu.ac.th | 081-8926690
5
6
7
8
9
10
11

## Project Charter
SAMPLE

## WBS with Gantt Chart BLANK (hidden)
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE | [6 empty] | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 20%
100%
90%
40%
70%
60%
50%
100%
30%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
CLICK HERE TO CREATE WBS OUTLINE AND DIAGRAM TEMPLATES IN SMARTSHEET