## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE
PROJECT TITLE | [12 empty] | COMPANY NAME
PROJECT MANAGER | [12 empty] | START DATE |  | 2020-09-23
PROJECT DURATION | [12 empty] | END DATE
[16 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
WBS NUMBER | TASK TITLE |  | TASK OWNER | [8 empty] | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[16 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation Phase | Customer | PM | BA | SA | DEV | SE | UX | QA | Trainer | IT Support
1.1 | Project Organization | [10 empty] | 15/08/2020 | 17/08/2020 | 3 | 100%
1.1.1 | Project Charter Revisions |  | P | [8 empty] | 17/08/2020 | 17/08/2020 | 1 | 100%
1.1.2 | Progress meeting # 2 |  | P | P | P | P | P | P |  |  | P | 17/08/2020 | 17/08/2020 | 1 | 100%
1.2 | HW, SW and Network preparation |  | P | [8 empty] | 17/08/2020 | 23/08/2020 | 7 | 100%
1.2.1 | Hardware and Network preparation | [5 empty] | P |  |  |  | P | 17/08/2020 | 23/08/2020 | 7 | 50%
1.2.2 | Software preparation |  |  |  |  | P | P |  |  |  | P | 17/08/2020 | 23/08/2020 | 7 | 0%
1.3 | Review Scope of work
1.3.1 | Scope of Work Revisions - Product Data |  | P | P | P | [6 empty] | 17/08/2020 | 23/08/2020 | 7 | 50%
1.3.2 | Scope of Work Revisions - Operation for Admin |  | P | P | P | [6 empty] | 17/08/2020 | 21/08/2020 | 5 | 100%
1.3.3 | Scope of Work Revisions - Operation for Customer |  | P | P | P | [6 empty] | 17/08/2020 | 21/08/2020 | 5 | 100%
2.1 | Requirement Gathering
2.1.1 | Get Requirement & Discussion |  |  | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14
ในฐานะแอดมิน
| สามารถสนทนากับลูกค้าผ่านช่องทางแอปพลิเคชั่นได้ |  |  | P
| สามารถสร้างรหัสส่วนลดให้ลูกค้า |  |  | P
| สามารถเพิ่มข้อมูลเซ็ตชาบูลงในเมนูได้ |  |  | P
| สามารถแก้ไขเซ็ตชาบูในเมนูได้ |  |  | P
| สามารถลบเซ็ตชาบูออกจากเมนูได้ |  |  | P
| สามารถเพิ่มส่วนลดให้ลูกค้าได้ |  |  | P
| สามารถแก้ไขรหัสส่วนลดได้ |  |  | P
| สามารถลบรหัสส่วนลดได้ |  |  | P
ในฐานะลูกค้า
| สามารถล็อคอินเข้าสู่ระบบได้ |  |  | P
| สามารถแก้ไขข้อมูลส่วนตัวได้ |  |  | P
| สามารถเลือกเซ็ตชาบูได้ |  |  | P
| สามารถแก้ไขออเดอร์ในตะกร้าสินค้าได้ |  |  | P
| สามารถยกเลิกออเดอร์ได้ |  |  | P
| สามารถเลือกเวลาในการจัดส่งได้ |  |  | P
| สามารถเลือกตำแหน่งในการจัดส่งได้ |  |  | P
| สามารถกรอกรหัสส่วนลดได้ |  |  | P
| สามารถให้คะแนนร้านชาบูได้ |  |  | P
| สามารถสนทนากับแอดมินผ่านช่องทางแอปพลิเคชั่นได้ |  |  | P
2.1.2 | Requirement Development |  |  | P | P | [6 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.1.3 | Summarize Requirement & Meeting | P | P | P | [7 empty] | 2020-03-09 | 2020-03-09 | 1 | 100%
2.2 | Summarize Source of Data
2.2.1 | Define Data Source for Product Data | P | P | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.2.2 | Define Data Source for Operation | P | P | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
2.2.3 | Data Source Sign-off Meeting | P | P | P | [7 empty] | 18/08/2020 | 31/08/2020 | 14 | 100%
3 | Analysis and Design Phase
3.1 | System flow Design |  |  |  | P | [6 empty] | 2020-10-09 | 23/09/2020 | 14 | 0%
3.2 | User Interface Design | [6 empty] | P |  |  |  | 2020-10-09 | 23/09/2020 | 14 | 100%
3.3 | Architectural Design |  |  |  | P | [6 empty] | 2020-10-09 | 23/09/2020 | 14 | 0%
3.4 | Detailed Design |  |  |  | P | [6 empty] | 2020-10-09 | 23/09/2020 | 14 | 0%
3.5 | Develop SRS document |  |  |  | P | [6 empty] | 2020-10-09 | 23/09/2020 | 14 | 50%
3.6 | SRS Sign-off Meeting | P | P | P | P | [6 empty] | 2020-10-09 | 23/09/2020 | 14 | 0%
4 | Development Phase
4.1 | Software Development |  |  | P | P | P | P |  |  |  |  | 2020-12-09 | 16/10/2020 | 35 | 0%
4.1.1 | Unit Test & Debug - Customer Operation |  |  |  | P | P | P |  |  |  |  | 25/09/2020 | 29/09/2020 | 5 | 0%
4.1.2 | Unit Test & Debug - Admin Operation |  |  |  | P | P | P |  |  |  |  | 27/09/2020 | 2020-01-10 | 5 | 0%
5 | Software Integration Test (SIT) & UAT
5.1 | Develop test scenario & test case |  |  | P |  |  |  |  | P |  |  | 27/09/2020 | 2020-06-10 | 10 | 0%
5.2 | Prepare Test Environment | [5 empty] | P |  |  |  |  | 27/09/2020 | 2020-06-10 | 10 | 0%
5.3 | System deployment on Test Environment |  |  | P |  |  | P |  |  |  |  | 27/09/2020 | 2020-06-10 | 10 | 0%
5.4 | Develop UAT documentation |  |  | P |  |  |  |  | P |  |  | 27/09/2020 | 2020-06-10 | 10 | 0%
5.5 | Training for UAT session |  | P | P | [5 empty] | P |  | 27/09/2020 | 2020-06-10 | 10 | 0%
5.6 | UAT |  | P | P | [5 empty] | P |  | 27/09/2020 | 2020-06-10 | 10 | 0%
5.7 | UAT Sign-off Meeting |  | P | P | [5 empty] | P |  | 27/09/2020 | 2020-06-10 | 10 | 0%
6 | Key User Training
6.1 | Develop administrator guide |  |  | P |  | P | [5 empty] | 2020-09-10 | 18/10/2020 | 10 | 0%
6.2 | Develop maintenance plan documentation |  | P | P | P |  | P |  |  |  |  | 2020-09-10 | 18/10/2020 | 10 | 0%
6.3 | Administrator training |  | P | P | [5 empty] | P |  | 20/10/2020 | 24/10/2020 | 5 | 0%
7 | Deployment Phase (Cut over) & Go-Live
7.1 | Prepare Production Environment |  |  | P |  |  | P |  |  |  |  | 26/10/2020 | 30/10/2020 | 5 | 0%
7.2 | Preliminaries + briefing + reserving resources (Check point, Go/NoGo) | P | P | P |  |  | P |  |  |  |  | 26/10/2020 | 30/10/2020 | 5 | 0%
7.3 | Timespan from 5 to 1 days before deployment (Check point, Go/NoGo) | P | P | P | [7 empty] | 26/10/2020 | 30/10/2020 | 5 | 0%
7.4 | Cut over (Check point, Go/NoGo) | P | P | P | [7 empty] | 26/10/2020 | 30/10/2020 | 5 | 0%
7.5 | Production test/authentication (Check point, Go/NoGo) | P | P | P | P | P | P |  |  |  |  | 2020-04-11 | 2020-08-11 | 5 | 0%
7.6 | First day in production use (Check point, Go-Live) | P | P | P | P | P | P |  |  |  |  | 2020-04-11 | 2020-08-11 | 5 | 0%
7.7 | Second day in production use (Check point, Go-Live) | P | P | P | P | P | P |  |  |  |  | 2020-04-11 | 2020-08-11 | 5 | 0%
7.8 | Support after Go-Live | [9 empty] | P | 2020-10-11 | 2021-09-11 | 365 | 0%
8 | Project Closeout (2 weeks)
8.1 | Closeout delivery |  |  | P | [7 empty] | 2020-02-12 | 2020-07-12 | 5 | 0%
8.2 | Close contract |  |  | P | [7 empty] | 2020-02-12 | 2020-07-12 | 5 | 0%
8.3 | Activate maintenance and technical support |  |  | P | [7 empty] | 2020-02-12 | 2020-07-12 | 5 | 0%
8.4 | Create project completion report |  |  | P | [7 empty] | 2020-02-12 | 2020-07-12 | 5 | 0%
8.5 | Project Closeout Meeting |  | P | P | [7 empty] | 2020-11-12 | 15/12/2020 | 5 | 0%
Note on Q7: Key % of task complete in cell and then it will generate colour bar automatically.

## Project Structure
PROJECT ORGANIZATION
PROJECT TITLE |  | Shabu For U |  | COMPANY NAME | Shabu For U
PROJECT MANAGER |  | Miss Kannika Thongnum |  | DATE | 2020-09-18
No | Name (EN) |  | Position in Project | Department/Division | E-mail | Phone
CUSTOMER
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
No | Name (EN) |  | Position in Project | Department/Division | E-mail | Phone
VENDOR
1 | Mr.Wattana | Pongpaew | Trainer , Quality Assurance |  | s6130613027@phuket.psu.ac.th | 063-0809112
2 | Mr.Sorravit | Thongsong | Developer , System Engineer / IT Support |  | s6130613028@phuket.psu.ac.th | 095-1716431
3 | Miss Kannika | Thongnum | Project Manager , System Analyst |  | s6130613036@phuket.psu.ac.th | 091-0487040
4 | Mr.Nutthapon | Nisakon | UX/UI Design , Business Analyst |  | s6130613048@phuket.psu.ac.th | 081-8926690
5
6
7
8
9
10
11

## Project Charter
SAMPLE

## WBS with Gantt Chart BLANK (hidden)
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE | [6 empty] | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 20%
100%
90%
40%
70%
60%
50%
100%
30%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
CLICK HERE TO CREATE WBS OUTLINE AND DIAGRAM TEMPLATES IN SMARTSHEET